## Sheet1
Requirement | Task | Member | Describe | Done | Percent complete
| Introduction | Võ Trần Huy Thông,Nguyễn Hữu Phúc | Introduction Toeic exam | Y | 100%
| High requirement | Võ Trần Huy Thông,Nguyễn Hữu Phúc | The requirement toeic exam | Y | 100%
| Functional requirement | Võ Trần Huy Thông,Nguyễn Hữu Phúc | Module Functional requirement | Y | 100%
| Non-functional requirement | Võ Trần Huy Thông,Nguyễn Hữu Phúc | List and detail non-functional requirement | Y | 100%
| System constraint | Võ Trần Huy Thông,Nguyễn Hữu Phúc | UI require / Other require | Y | 100%
Test
Design
| Module Design | Nguyễn Đinh Nhật Minh | Design partern | Y | 100%
| Database Design | Nguyễn Đinh Nhật Minh | Design partern | Y | 100%
| User Interface | Nguyễn Đinh Nhật Minh | Design partern | Y | 100%
Code | Connect.php | Phạm Cao Nam Hải, Đỗ Đức Duy | To connect to the database | Y | 100%
| dangki.php | Phạm Cao Nam Hải, Đỗ Đức Duy | Code php file to design layout follow design | Y | 100%
| dangnhap.php | Phạm Cao Nam Hải, Đỗ Đức Duy | Code php file to design layout follow design | Y | 100%
| dangxuat.php | Phạm Cao Nam Hải, Đỗ Đức Duy | Code php file to design layout follow design | Y | 100%
| detailpage.php | Phạm Cao Nam Hải, Đỗ Đức Duy | Detailed lesson content page | Y | 100%
| header.php | Phạm Cao Nam Hải, Đỗ Đức Duy | Including login and registration | Y | 100%
| index.php | Phạm Cao Nam Hải, Đỗ Đức Duy | Code php file to design home page | Y | 100%
| thitoeic.sql | Phạm Cao Nam Hải, Đỗ Đức Duy | Database of Sakai Toeic | Y | 100%%